## Functional Execution
CartSure Functional Testing Execution Report
Test Case ID | Module | Scenario | Test Steps | Expected Result | Actual Result | Status | Severity | Executed By | Remarks
TC_001 | Login | Valid Login | 1. Open CartSure application 2. Navigate to Login page 3. Enter valid username and password 4. Click Login button | User logs in successfully | User logged in successfully | Pass | Low | QA Tester | Working as expected
TC_002 | Login | Invalid Login | 1. Open Login page 2. Enter invalid username and password 3. Click Login button | Error message should display | Proper validation message displayed | Pass | Low | QA Tester | Negative scenario validated
TC_008 | Search | Search Product | 1. Open Search bar 2. Enter product keyword 'Laptop' 3. Click Search button 4. Verify search results | Relevant products displayed | Products displayed correctly | Pass | Low | QA Tester | Search working correctly
TC_013 | Cart | Add Product to Cart | 1. Open Product page 2. Select iPhone product 3. Click Add to Cart button 4. Verify product added in cart | Product should add to cart | Product added successfully | Pass | Medium | QA Tester | Cart working correctly
TC_015 | Cart | Update Quantity | 1. Open Cart page 2. Increase product quantity 3. Click Update button 4. Verify updated quantity | Quantity should update | Quantity updated correctly | Pass | Medium | QA Tester | Quantity update validated
TC_019 | Checkout | Checkout Process | 1. Open Cart page 2. Click Proceed to Checkout 3. Add shipping address 4. Continue to payment page | Checkout page should load | Checkout page loaded | Pass | High | QA Tester | Checkout flow validated
TC_023 | Payment | Successful Payment | 1. Open Payment page 2. Select payment method 3. Enter valid card details 4. Click Pay Now 5. Verify successful payment | Payment successful | Payment completed successfully | Pass | Critical | QA Tester | Payment gateway working
TC_024 | Payment | Failed Payment | 1. Open Payment page 2. Enter invalid card details 3. Click Pay Now 4. Verify payment failure message | Error message displayed | Application crashed during payment | Fail | Critical | QA Tester | Bug logged as BUG_04
TC_025 | Order | Order Confirmation | 1. Complete order process 2. Verify order confirmation page 3. Verify Order ID generated | Confirmation page displayed | Confirmation page displayed | Pass | High | QA Tester | Order confirmation validated

## Regression Report
CartSure Regression Testing Report
Test Case ID | Module | Scenario | Status | Executed On | Remarks
TC_01 | Login | Valid Login | Pass | 01-Aug-2026 | Stable
TC_02 | Search | Search Product | Pass | 01-Aug-2026 | Stable
TC_03 | Cart | Add to Cart | Pass | 01-Aug-2026 | Working correctly
TC_04 | Cart | Remove Item | Pass | 01-Aug-2026 | Validated
TC_05 | Cart | Update Quantity | Pass | 01-Aug-2026 | Working correctly
TC_06 | Checkout | Checkout Process | Fail | 01-Aug-2026 | Checkout crash issue
TC_07 | Payment | Payment Gateway | Pass | 01-Aug-2026 | Payment stable
TC_08 | Order | Order Confirmation | Pass | 01-Aug-2026 | Validated

## Defect Report
CartSure Defect Tracking Report
Defect ID | Description | Severity | Previous Status | Retest Result | Final Status | Remarks
BUG_01 | Add to Cart not working | High | Fixed | Pass | Closed | Issue resolved successfully
BUG_02 | Checkout error | Critical | Fixed | Fail | Reopened | Issue still reproducible
BUG_03 | Quantity update issue | Medium | Fixed | Pass | Closed | Validated after fix
BUG_04 | Checkout page crash | Critical | Open | Pending | Open | Needs immediate attention
BUG_05 | Incorrect total price | High | Open | Pending | Open | Calculation mismatch observed